## Sheet1
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Defect Count | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_REGESTRATION_003 | Home | It is found that insert photo field is is accepting a photo of size more than 150 kb. | "Detailed Description: It is found that insert photo field is is accepting a photo of size more than 150 kb. Steps to produce the bug: 1. Open Browser 2. Enter URL for the website 3.Click on ""New registration on Portal"" 4.Go to ""Personal Information"" 5.clikc on option ""Insert photo"" field 6.insert photo of size more than 150 kb 7.Click on upload button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the insert photo field is accepting photo of size more than 150 kb.Inserted photo is exceeding the mandatory limit of photo size. " | Coding | Internet Explorer | Internal Dev | P2 | Low | 1.1.3 | 3 | 1/23/2019 | Akash Bargode |  | ACT |  | TC_REGESTRATION_003
DF_REGESTRATION_005 | Home | It is found that application is not able generate and display the Registration ID upon successful registration process. | "Detailed Description: It is found that application is not able generate and display the Registration ID upon successful registration process. Steps to produce the bug: 1. Open Browser 2. Enter URL for the website 3.Click on ""New registration on Portal"" 4.Enter all mandatory Fields 5.Click on ""save and submit"" Actual result observed on running above steps: On executing the above mentioned steps it is observed that on clicking save and submit button its submitting form but not generating and displaying Registration ID as expected. " | Coding | Internet Explorer | Internal Dev | P0 | High | 1.1.5 | 5 | 1/23/2019 | Akash Bargode |  | ACT |  | TC_REGESTRATION_005